# CDS Family & Behavioral Health Services, Inc.

Strategic Five Year Plan

Year Four– FY 2010-2011

Report

December 2010

# This publication can be made available in multiple media formats upon request.

| Mission “Strengthening Communities by Building Strong Families” |
| --- |
| Geographical Area: Alachua, Baker, Bradford, Columbia, Dixie, Gilchrist, Hamilton, Lafayette, Levy, Madison, Putnam, Suwannee, Taylor and Union Counties |  |

| CDS 1218 NW 6th Street GAINESVILLE, FL 32601 (352) 244-0628 |  |
| --- | --- |

# Report  2010/2011

Process:

# Strategies:

# I.  Strengthen Quality Care for FY 2010/2011.

| Goals | Objectives | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| a. Improve the clinical skills of staff providing direct services to participants | a.1. Clearly articulate which therapeutic interventions staff should be familiar with including recognizing and caring for participants with co-occurring disorders a.2.Determine competencies staff currently possess with therapeutic interventions (including analysis of the COMPASS & CODECAT) a.3. Have Counseling staff participate in Trauma Informed Care Training a.4. Address deficiencies identified through training, peer review, quality assurance reviews and supervision | SAMH/CINS Managers Clinical Supervisors SAMH/CINS Managers & Peggy Vickers SAMH/CINS Managers | 1/11 Ongoing 1/11 Ongoing |  | Managers determined what interventions were being used in 11/10 |
| b. Improve efforts to manage participants appropriately | b.1. Ensure staff understand procedures to manage participants with suicidal ideation and other crisis symptom’s, including but not limited to appropriate interventions, levels of supervision and notification b.2. Ensure cases are properly transferred between counselors, programs and other agencies b.3. Identify key safety practices and ensure staff fully understand and comply with responsibilities | SAMH/CINS Managers SAMH/CINS Managers SAMH/CINS Managers | 2/11 2/11 3/11 |  | Procedures will be reviewed at staff meetings Procedures will be reviewed in staff meetings Procedures will be reviewed in staff meetings |
| c. Enhance our ability to engage participants | c.1. Assess our skills and processes to welcome participants c.2. Review data to determine by counselor length of stay, case disposition status & participant satisfaction c.3. Role model best practices | SAMH/CINS Managers Peggy Vickers. Estela Rosa, SAMH/CINS Managers | 5/11 |  |  |
| d. Increase focus on maintaining a safe environment | d.1 Periodically assign different staff to assess safety issues |  | 2/11 |  | Each Site designate and have a staff person to do a safety walk through this month |
| e. Improve documentation related to interactions with participants | e.1. Provide staff a training guide to properly use BIRP e.2. Develop with staff samples of Individual Plans and Transition Plans e.3 Ensure staff keep these tools readily available e.4. Give staff periodic feedback on documentation e.5 Encourage the use of computers in producing documentation | Sam Clark, PeggyVickers & Leslie Frost Sam Clark, Peggy Vickers & Leslie Frost SAMH/CINS Managers SAMH/CINS Managers SAMH/CINS Managers | 11/10 3/11 4/11 Monthly Ongoing |  | A guide was developed & provided to staff 11/10 for feedback An Individual Plan Guide was developed & distributed 11/10 to staff for feedback |
| f. Enhance compliance with meeting productivity standards | f.1. Identify the expectations and share with staff f.2. Identify the actions to be taken when expectations are achieved or not achieved f.3. Be consistent in the utilization of these processes | Sam Clark, Estela Rosa & SAMH/CINS Managers Sam Clark SAMH/CINS Managers Sam Clark SAMH/CINS Managers | 7/10 Ongoing Ongoing |  | Action Plans should be developed on a bi-monthly basis for low performance |
| g. Achieve Contractual Outcomes | g.1. Ensure staff are familiar with contractual requirements g.2. Ensure staff understand their specific role in achieving outcomes g.3. Maintain accountability | SAMH/CINS Managers SAMH/CINS Managers SAMH/CINS Managers | 7/10 7/10 Ongoing |  |  |

# II. Design and operationalize a plan to maintain a significant portion of the current level of Prevention of funding FY 2011/2012.

| Goals | Objectives | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Enhance and support coalitions within our service area | a.1. Maintain a leadership role in the PIPSA Coalition and ensure that CDS is appropriately positioned to address identified needs through providing evidence based programs a.2. Ensure the Levy County Coalition is positioned to receive funding and that CDS is appropriately positioned to address identified needs through providing evidence based programs a.3. Determine the level of appropriate involvement with other area coalitions | Gwen Love & Sam Clark Gwen Love & Sam Clark Gwen Love & Sam Clark | 5/11 5/11 5/11 |  |  |
| Identify new programs that address community needs | b.1. Solicit information about programs in use from other providers b.2. Review evidence based programs through NREPP, SAMSAs National Registry of Evidence-based Programs and Practices | Gwen Love & Sam Clark Gwen Love & Sam Clark | 11/10 11/10 |  | Gwen Love made a site visit to EPIC to review the SUCCESS program Gwen & Sam met with Reichert House personnel to discuss NREPP options. |
| Create partnerships to facilitate program implementation | c.1. Consider responding to the SAMH Prevention Invitation to Negotiate (ITN) with Meridian and other relevant providers c.2. Develop opportunities for Program implementation in the Alachua and Levy County School systems | Sam Clark Gwen Love, Sam Clark & Jim Pearce |  |  | Sam Clark met with Richard Anderson from Meridian and subsequently with SAMH Program staff. The ITN is off the table based on the provider’s willingness to negotiate. Jim Pearce met with Alachua County School & DCF personnel and other interested parties to discuss opportunities in Alachua County schools which appear to exist. |
| Implementing new programs with fidelity | d.1. Ensure staff are properly trained and positioned to implement programs | Gwen Love | 7/11 |  |  |

# III. Focus on Outreach and Access efforts to achieve agency objectives FY 2010/2011.

| Goals | Objectives | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| a. Promote our name and mission within the community to increase access & reduce barriers to services | a.1.Ensure all staff are familiar with our name and our mission | All Staff | Ongoing |  |  |
| b. Work with information & referral outlets to ensure CDS is properly identified | b.1. Contact media and telephone directory outlets to ensure that CDS is properly identified | Sam Clark & Estela Rosa | 11/10 | 12/10 | We were successful in increasing the accuracy and advertising in the AT&T telephone directory, but only made limited headway in correcting errors in the Edge Book. Sam has made contact with I&R in the Central & East regions & the National SAMSHA Directory to ensure our listings are correct |
| c. Identify how we want to promote our name to the public | c.1. Agree upon appropriate representations of CDS in print media c.2. Agree upon appropriate representations of CDS when answering telephones C.2. Ensure all CDS computers and voice mails are set up with a consistent message c.4. Train staff and volunteers accordingly | Managers Managers Estela Rosa/ Ryan Pendry SAMH/CINS Managers & Radha Selvester | 1/11 2/11 |  | A greeting should have 3 elements; a. The greeters name b. CDS and the program name c. May I help you? |
| d. Expand the public’s knowledge of our correct addresses and telephone numbers | d.1. Make sure that this information is properly and prominently displayed on all CDS materials and press releases | Sam Clark & Radha Selvester | 2/11 |  |  |
| e. Target outreach efforts to populations most likely to result in increased referrals | e.1. Work the outreach plans developed at the program and regional level | SAMH/CINS Managers, Radha Selvester | Bi-Monthly |  |  |
| f. Legislative Advocacy | f.1. Target program information to key elected officials and other leaders and stakeholders f.2. Use the Annual Report as an Advocacy tool f.3. Identify participants and others who can speak to the need for services f.4. Identify success stories | Jim Pearce, Sam Clark & Radha Selvester Jim Pearce, Sam Clark & Radha Selvester SAMH/CINS Managers | 12/10-3/11 |  | Sam attended and distributed material to our local delegation. Jim and Sam continue to work with the Florida Network and FADAA respectively. Legislative materials were shared with the CDS Board 12/10. |

# IV. Position CDS to appropriately respond to opportunities related to Health Care Reform FY 2010/2011.

| Goals | Objectives | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| a. Develop new partnerships | a.1. Create relationships with primary health care providers a.2. Create relationships with insurance vendors | Sam Clark & Managers Sam Clark/Peggy Vickers | 12/10 4/11 |  | Sam, Leslie, Estela & Peggy completed the 6 part Boot Camp series sponsored by DCF/FADAA to prepare for Health Care reform and have developed several relationships with other providers from these meetings. The CDS Medicaid application has been submitted and has been returned twice for revisions. We continue to stay current with Magellan requirements. We are in the process of setting up meetings QHC’s |
| b. Improve infrastructure to respond to the needs of paying participants | b.1. Assess need for additional staff, adjusting schedules of current staff, cross training, redefining duties, reassignments b.2. Assess facility needs | Sam Clark, Estela Rosa, Leslie Frost & Peggy Vickers | 6/11 |  |  |
| c. Ensure data collection systems meet the requirements of third party payers | c.1. Fully comprehend requirements and associated procedures c.3. Establish quality assurance protocols | Sam Clark, Estela Rosa & Peggy Vickers Sam Clark, Estela Rosa, Leslie Frost & Peggy Vickers | 7/11 7/11 |  |  |
| d. Ensure staff are appropriately trained and credentialed | d.1. Train staff in new procedures d.2. Identify incentives for staff based on new revenue streams | SAMH/CINS Managers Sam Clark & SAMH/CINS Managers | 7/11 |  |  |